## ProjectSchedule
CS2024 Smart Tuition Web Development Project
Smart Tuition
Goh Jun Bin, Jack Teo, Joy Ng, Ang Chen Fang |  |  | Project Start: | 2021-10-14 |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  | Display Week: | 1 |  |  | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-10-11 to 2021-12-05
MEETING | TASKS | REMARKS | PROGRESS | START | END | DAYS | time axis 2021-10-11 to 2021-12-05
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Planning and Design Phase
1 | Initialisation - Kickoff Meeting | Project scope and role assignment | 100% | 2021-10-14 | 2021-10-14 | 1
| Research | Market comparisons, design considerations | 100% | 2021-10-14 | 2021-10-19 | 6
2 | Preparation for Development Phase | Division of labour | 100% | 2021-10-20 | 2021-10-20 | 1
| Wireframing |  | 100% | 2021-10-20 | 2021-10-20 | 1
| Web content planning | Marketing and promotions | 100% | 2021-10-20 | 2021-10-20 | 1
| Code Environment Setup | GitHub included for version control and coordination | 100% | 2021-10-20 | 2021-10-20
Development Phase
- | Assets creation | Logo, icons and graphics | 70% | 2021-10-21 | 2021-10-31 | 11
- | Front end development | Work based on assigned tasks | 70% | 2021-10-21 | 2021-10-31
- | Back end development | Work based on assigned tasks | 70% | 2021-10-21 | 2021-10-31 | 11
3 | Team meeting checkpoint | Sync up on progress, clear doubts and re-calibrate goal if needed |  | 2021-11-01 | 2021-11-01 | 1
| PDPA, SEO implementation discussion | Additional features to implement |  | 2021-11-01 | 2021-11-01 | 1
- | Continued web development | Work based on assigned tasks |  | 2021-11-02 | 2021-11-10
4 | Team meeting checkpoint | Integration of all programming work |  | 2021-11-11 | 2021-11-11
| Soft launch on test server | Soft launch onto platform |  | 2021-11-11 | 2021-11-11 | 1
Review Phase
4 | Review | QA and bug fix (e.g. responsiveness) |  | 2021-11-11 | 2021-11-13 | 3
| Polish | Final touch ups and changes |  | 2021-11-11 | 2021-11-13 | 3
5 | Creative brief slides | Documentation |  | 2021-11-13 | 2021-11-14 | 2
| Web Launch | Push changes onto live server |  | 2021-11-14 | 2021-11-14
| Final Testing |  |  | 2021-11-14 | 2021-11-14
Formulas:
Week 1 = [Week 1, row below]
Week 2 = [Week 2, row below]
Week 3 = [Week 3, row below]
Week 4 = [Week 4, row below]
Week 5 = [Week 5, row below]